Seedling: A Data-Driven Architecture for Cost Mitigation and Adoption

Kate Herrick Capella University IT-FPX 4998: Capstone II Site Supervisor: Angela Baughman November 15, 2025

Executive Summary: Project "Seedling"

The Greenfield Financial Seedling Initiative was launched to address the organization’s single largest operational expenditure: the millions of dollars spent annually on manual transcription labor for client balance sheets. Market research and internal cost analysis suggest that successfully migrating clients to a digital self-service portal could yield cost savings exceeding $2.5 million in the first year against a planned spend of $550,000. While the primary driver is financial, the project's focus has been revised to focus on the development of a solution that also mitigates data integrity risk stemming from the institution's error-prone manual process. An initial review of current-state processes confirmed that relying on human data entry violates the Single Source of Truth (SSOT) principle, compromising data fidelity and business intelligence.

The initiative's core objectives are threefold:

- To achieve cost mitigation and ROI by embedding a mandatory, non-negotiable Client Adoption Checkpointinto the project lifecycle, ensuring the business takes ownership of the shift to self-service.

- To enhance employee well-being and data integrity by replacing error-prone manual transcription with an automated ETL data pipeline and establishing Salesforce as the SSOT for client financial data.

- To secure the Primary Lineage Point (PLP) of the data at the client input screen, preventing data corruption and creating a superior, auditable record.

Project Lifecycle and Milestones

The Seedling Initiative is executed using a Hybrid Agile/Waterfall methodology, strategically front-loading the most critical risk mitigation work (data governance and SME-intensive requirements) into the Waterfall phase. The overall timeline is designed for a twelve-month delivery, focusing first on data integrity and risk mitigation, followed by client-facing feature development and aggressive adoption campaigns.

| Milestone | Timeframe | Description and Deliverables |
| --- | --- | --- |
| T+1 Month: Strategic Planning & Resource Advocacy | T+1 Month | Project Initiation and Charter Approval. Formal approval of the budget, resources, and the Hybrid execution model. Key deliverable: Executive Mandate for SME Time secured via the Project Sponsor, directly mitigating the highest resource risk. |
| T+3 Months: Data Governance & PLP Definition (Waterfall Phase) | T+3 Months | Requirements and Data Mapping Completion. Finalization of all business, technical, and data governance requirements. Key deliverable: 100% Data Field Mapping for the ETL pipeline, official designation of the Primary Lineage Point (PLP) at the client portal, and approval of all automated validation rules. |
| T+6 Months: Technical Build Completion (Agile Sprints) | T+6 Months | SSOT and ETL Pipeline Deployment. Full development and internal testing of the Salesforce SSOT architecture and the automated ETL pipeline connecting the client portal to Salesforce. Key deliverable: SSOT Go-Live (internal only). |
| T+8 Months: Client Portal UI/UX Finalization | T+8 Months | Client Portal Development & Integration Testing. Completion of the client-facing portal UI/UX, built around the principle of Perceived Ease of Use (PEU), and successful integration with the ETL pipeline. Key deliverable: 100% Data Validation Testing of the entire data flow. |
| T+10 Months: Adoption Readiness & Approval Gate | T+10 Months | The Strategic Adoption Checkpoint. Mandatory non-technical gate requiring sign-off from Client Services and Marketing. Deliverables: Finalized Client Communication Plan and Dedicated Adoption Budget secured. This gate ensures project value is protected. |
| T+12 Months: Production Launch & Closeout | T+12 Months | Go-Live. Production launch of the client portal and formal retirement of the paper submission process. Hand-off to Operations and Closeout. |

Architectural Foundation and Business Value

The success of the Seedling Initiative rests on the strategic implementation of data architecture principles to realize business value:

Single Source of Truth (SSOT) and ETL: The project fundamentally shifts data ownership. The Salesforce platform is designated as the SSOT for client balance sheet data, consuming the structured input from the client portal via the ETL pipeline. This architecture eliminates data silos, ensures every internal stakeholder—from relationship managers to credit analysts—accesses the same validated information, and is critical for improving business intelligence.

The Primary Lineage Point (PLP): By enforcing data collection through the client portal, the project formally establishes the PLP at the point of client entry. This is the first, most critical step in data governance, ensuring a clean, auditable, and reliable origin for the data. This structural change is what eliminates the inherent risk of the previous manual process.

Ethical and Employee Benefit: The automation eliminates the need for employees to work late nights and weekends during the peak submission season (January). This positive impact on employee well-being and work-life balance is a significant ethical benefit of the project, allowing staff to reallocate their time to higher-value client relationship activities rather than low-value transcription tasks.

Risk and Communication Strategy

The highest-priority threats to project delivery are low client adoption and Subject Matter Expert (SME) resource constraints. These are actively mitigated by executive action and governance controls.

Risk Mitigation:

- Low Client Adoption Risk: This is the greatest risk to realizing ROI. It is actively addressed by the Strategic Adoption Checkpoint at T+10 Months, which transfers accountability for achieving the 80% adoption target to the Client Services and Marketing teams.

- SME Resource Constraints: This technical risk is mitigated by the Executive Mandate for SME Time secured in the T+1 Month milestone. By executing the critical data mapping as a front-loaded Waterfall phase, the Project Manager strategically leverages the organizational priority of the project to compel resource allocation for necessary non-glamorous work.

Stakeholder Communication: Stakeholder communication is tailored by audience and frequency to maintain focus on the core objectives of cost mitigation and adoption.

- Steering Committee (Executive): Will receive bi-weekly briefings focused primarily on Adoption Checkpoint readiness, cost-saving projections, resource concerns, and formal sign-off requests.

- Business Stakeholders (Client Services/Marketing): Will be furnished with weekly status reports that detail client portal UI/UX development status, adoption campaign progress, and metrics related to Perceived Ease of Use (PEU).

- Technical Teams (IT/DevOps): Will hold daily meetings focused on integration, SSOT development, and ETL validation testing, ensuring the technical integrity of the data pipeline remains the central focus.

This disciplined communication structure ensures that the critical link between the client experience and the multi-million dollar business case remains transparent to all leaders, providing a clear and managed path to strategic success.