Project Charter

| Project Name | “Gateway” |
| --- | --- |
| Department | - Digital Experience Marketing - Information Technology |
| Focus Area | - Prospect Experience - Compliance and Risk Mitigation |
| Product/Process | Prospect Financial Cost Calculator with Integrated Data |
| Prepared By | Kate Herrick, Project Manager |

Project Charter Version Control

| Version | Date | Author | Change Description |
| --- | --- | --- | --- |
| 1.0 | October 24, 2025 | K. Herrick | Initial draft |

- Project Charter Purpose

The purpose of this project is to successfully implement a prospect-facing cost calculator component on Arborwood University’s commercial websites and paid media pages. The core goal is to address the critical market gap related to cost transparency that impedes prospect conversion. This project is explicitly chartered to design and enforce a formal Legal and Compliance Gateway to secure approval before development proceeds, thereby mitigating the litigation risk identified as the single largest threat to the solution’s viability. Additionally, the project will implement new, automated data integration infrastructure to ensure calculation accuracy and reduce long-term maintenance labor.

- Project Executive Summary

This charter outlines the plan to build a solution suitable for web page implementation that allows prospective baccalaureate, master's, and certificate students to estimate their degree cost and time commitment based on transfer credits, scholarship and other savings opportunities, and the prospective student’s intended enrollment pace. This is a strategic imperative designed to capture an estimated $8.9 million annual revenue increase in the first year following deployment. The project is structured specifically to overcome two organizational challenges identified in the SWOT analysis:

- The necessity of legal approval to comply with consumer protection and financial aid regulations and to avoid litigation.

- The need for data integration to ensure the real-time accuracy required for compliance.

Success is defined not only by technical delivery, but by securing and maintaining a renewable certification of legal approval for the component's functionality and content.

- Business Needs

Drivers for this project include:

| Impetus | Rationale |
| --- | --- |
| Conversion Improvement | The lack of personalized cost transparency is the single biggest obstacle preventing prospects from requesting additional information on the commercial website. |
| Risk Mitigation | Regulatory and litigation risk associated with inaccurate or misleading financial projections has been a historical obstacle to the adoption of similar solutions. This project must resolve that risk. |
| Competitive Differentiation | There is a clear market opportunity to create a "best-in-class" tool, as competitors rely on static tuition tables. |
| Data Integrity and Efficiency | The need for accurate, real-time calculation data requires replacing current manual processes with automated data fetches from core student administration systems. |

- Business Case

The project will address both a strategic market opportunity and a critical compliance threat. By implementing a cost calculator solution, Arborwood is positioned to capture an estimated $8.9 million revenue increase in Year 1 (a 10% corporate revenue growth) and a potential $39 million gain over the solution's lifespan, based on a minimal estimated investment spend of $425,000. Successful implementation requires the investment in Compliance Governance (the formal legal gateway) to ensure the technical solution is legally viable and maintainable.

- Project Requirements

Legal Compliance Gateway: Mandatory, documented approval from the Legal organization must be obtained before development begins. This process must be rigorous enough to mitigate risks related to FTC and DoE consumer protection laws, as well as third-party or class action litigation related to fraud or misrepresentation.

Data Integration: A new API call and data storage component must be developed to retrieve real-time, accurate cost data from the University’s core student administration systems.

Component Functionality: The solution is planned to be a multi-step “wizard” component in Adobe Experience Manager (AEM), providing estimates for cost, time, remaining credits, and savings for baccalaureate, master's, and certificate programs.

Content Customization: Content producers must be able to customize disclaimers, instructional copy, tool tips, and other supplemental content via the AEM authoring interface.

Output Accuracy: Calculations must correctly factor in tuition caps, scholarships, and transfer credit parameters for dozens of different degree programs.

- Configuration Management Requirements

Configuration management for this project will focus on the following key assets:

Project Documentation: All documents (Charter, Requirements, Calculation Use Cases and Legal Sign-Off artifacts) will be stored in Arborwood’s centralized, version-controlled project repository.

Code: All custom AEM component code, JavaScript logic, and API servlet code will be managed in Arborwood’s IT source control system.

Compliance Artifacts: The formal legal and compliance sign-off document for the calculator's content and logic will be versioned and stored with change traceability.

Change Management and Control: Any request for changes to the project scope, schedule, budget, or the calculation logic itself must be formally submitted, reviewed by the project’s Change Control Board (CCB), and must include re-approval from the Legal stakeholder(s).

- Project Boundaries

The scope of this project is limited to:

- Development, testing, and deployment of the custom cost calculator AEM component and its associated calculation logic.

- Development, testing, and deployment of the new API integration infrastructure to fetch real-time data from core student administration systems.

- Applicability is limited to baccalaureate, master's, and certificate programs only.

The project does not include:

- Development of calculator functionality for doctoral programs (due to timeline variability).

- Any changes to the core business logic or financial data within the student administration source systems.

- Marketing campaign execution or media ad buys associated with the component's launch.

- A/B or other competitive user experience testing in advance of solution deployment.

- Milestones

| Milestone | Target Completion Date |
| --- | --- |
| Project Charter Approval | January 2026 |
| Design Completion | February 2026 |
| Calculation Use Case Development | April 2026 |
| Detailed Requirements Completion | May 2026 |
| Legal/Compliance Gateway Sign-Off | June 2026 |
| API/Data Integration Build Completion | August 2026 |
| AEM Component Development Complete | November 2026 |
| System Testing and UAT | December 2026 |
| Production Launch | January 2027 |
| Project Closure and Post-Implementation Review | February 2027 |

- Work Breakdown Structure

1.0 Initiation and Planning

1.1	Project Charter Approval

1.2	Team Kickoff and Resource Allocation

1.3	Design Completion (High-Fidelity Mockups of Calculator Component)

2.0 Detailed Analysis and Legal Gating

2.1	Use Case and Calculation Logic Definition

2.2	Detailed Requirements Completion (Functional and Technical Specifications)

2.3	Data Mapping and API Specification with Student Administration Systems

2.3	Test Plan Development (Including Compliance Scenarios)

2.4	Legal and Compliance Review and Approval

3.0 Execution

3.1	Back-end API Servlet and Data Integration Build

3.2	New AEM Data Repository Component Development

3.3	AEM Calculator Component Development

3.4	API/Component Integration

4.0 Testing

4.1	Unit Testing

4.2	Integration Testing

4.3	End-to-End Testing

4.4	User Acceptance Testing (UAT)

4.5	Legal and Compliance Final UAT Checkpoint

5.0 Deployment and Closure

5.1	Production Deployment

5.2	Content Author Training

5.3	Post-Implementation Review & Lessons Learned

- Project Stakeholders

| Stakeholder | Organizational Role | Vested Interest/Impact |
| --- | --- | --- |
| Cain Redner | Project Sponsor/Digital Experiences Director | Final budget authoring and success metric accountability |
| Mike Goettl | Site Supervisor/IT Director | IT team leadership and deployment manager |
| Priyanka Singh | Legal Lead/Associate Counsel | Final legal and compliance authority |
| Erin Gallatin | Business Analyst | Defines use cases, calculation logic, data mapping requirements, and component configuration specifications |
| Akshay Subramanian | Technical Lead | Leads API and component development |
| Nicole Steinmetz | Content Production Lead | Coordinates and trains web authors |

- High Level Budget

| Project Expense | Estimated Cost | Rationale |
| --- | --- | --- |
| Labor - Business Analysis - IT Development - Testing | $325,000 | Eight-month, seven-person team development effort. |
| Legal and Compliance Evaluation and Approval | $75,000 | Dedicated risk assessment, including referral to outside counsel for secondary review. |
| Technology | $25,000 | Incurred costs of purchasing extensible functionality in AEM. |
| Total Estimated Cost | $425,000 | Required investment to achieve the $35M annual revenue increase. |

- Project Conditions

- Project Assumptions

- The funding and dedicated IT resources necessary for the entire development effort will be maintained and protected from being engaged for other marketing priorities.

- Designated legal and compliance stakeholders will dedicate the necessary time to perform the formal review and provide approval.

- The data integration team will have resources available on a timely basis to guide data mapping efforts if needed.

- The business owner of the core student administration systems will make resources available for table and field identification and other reference needs if required.

- The newly-delivered AEM component to be used as a repository for data that is retrieved via the newly-developed API can be configured as expected.

- Project Risks

Risk 1:

Regulatory Veto: The legal department may not approve the component under any circumstances, rendering the entire project unsalvageable, similar to the previous attempt.

Mitigation: Legal Gateway is a mandatory, early gate in the project that follows design, requirements finalization, and use case development so that legal stakeholders have all information regarding the solution’s function and logic prior to issuing approval.

Risk 2:

IT Skepticism: IT team's historical frustration with abandoned marketing projects may lead to resistance or disengagement.

Mitigation: Leadership must clearly communicate the permanent strategic value and commitment to the project. IT resources must be shielded from conflicting priorities and afforded the bandwidth they need to complete the project without interference.

Risk 3:

Data Integration Complexity: The API/source system integration may prove significantly more complex or costly than estimated, impacting the timeline and budget.

Mitigation: The need to provide legal stakeholders with full requirements and calculation use cases enables the team to begin analysis early in the project, enabling the team to begin prior to legal approval.

- Project Constraints

Compliance: The component must adhere to all federal, state, and institutional regulations regarding financial aid and cost transparency.

Timeline: The solution must be deployed by January 2027 so that anticipated revenue gains span the full fiscal year.

Scope: Limited to baccalaureate, master's, and certificate programs only.

Platform: Must be implemented as a custom component within the existing Adobe Experience Manager (AEM) platform.

- Acceptance Criteria

The project will be considered complete and successful when the following criteria are met:

- Formal, documented Legal and Compliance approval is secured for the calculator's content, logic, and disclaimers.

- The new API call successfully fetches and standardizes real-time cost data from core student administration systems.

- The AEM calculator component is fully deployed to production and successfully calculates the estimated cost and time to completion for all in-scope degree programs.

- The component demonstrates 100% functional accuracy across all tested financial and transfer scenarios defined in the use cases.

- Marketing content authors are fully trained and able to update non-logic content and disclaimers using the AEM authoring interface.

- Approval Requirements

Project approval will be granted when the Project Charter is signed by the designated approvers. Subsequent approvals required during the project lifecycle include:

- Approval of detailed requirements and design documents.

- Mandatory approval during the Legal/Compliance Gateway.

- Approval of the test plan and successful sign-off on User Acceptance Testing (UAT).

- Approval from the Executive Sponsor to proceed with production deployment.

15. Approvals

| Action | Name | Role | Date |
| --- | --- | --- | --- |
| Prepared By | Kate Herrick | Project Manager | October 24, 2025 |
| Approved By | Cain Redner | Project Sponsor/Digital Experiences Director |  |
| Approved By | Mike Goettl | Site Supervisor/IT Director |  |
| Approved By | Priyanka Singh | Legal Lead/Associate Counsel |  |
| Approved By | Nicole Steinmetz | Content Production Lead |  |